## Cost Plan
Sheet1
Resource Sheet
| S.no | Resource | Quantity | Hours Worked | Pay Per Hour | Hours per Resource | Labour Cost | Overhead Cost | Total Cost
| 1 | Project Manager | 2 | 240 | 100 | 120 | 24000 | 3600 | 27600
| 2 | Technical Writer | 1 | 112 | 60 | 112 | 6720 | 1008 | 7728
| 3 | Interviewer | 1 | 24 | 40 | 24 | 960 | 144 | 1104
| 4 | Software Engineer | 3 | 64 | 100 | 21.33 | 6400 | 960 | 7360
| 5 | Designer | 2 | 96 | 130 | 48 | 12480 | 1872 | 14352
| 6 | Senior Manager | 1 | 16 | 120 | 16 | 1920 | 288 | 2208
| 7 | Analyst | 1 | 8 | 80 | 8 | 640 | 96 | 736
| 8 | Software Requirement Engineer | 2 | 80 | 90 | 40 | 7200 | 1080 | 8280
| 9 | HR | 1 | 16 | 100 | 16 | 1600 | 240 | 1840
| 10 | Database Developer | 1 | 56 | 100 | 56 | 5600 | 840 | 6440
| 11 | DevOps Engineer | 2 | 32 | 100 | 16 | 3200 | 480 | 3680
| Total Cost of All the Resources Consumed | [7 empty] | 81328
Sheet 2
Total Budget Sheet
| S.no | Budget Entity | Units | Per Unit Cost | Total Cost | Net Total | Percentage of Total Budget
| 1 | Labour Cost |  |  |  | 81328 | 40.2% | (As calculated in Sheet 1)
| 2 | Component Cost |  |  |  | 1301 | 0.64%
| 2.1 | AWS EC2 | 2 | 0.5 | 1
| 2.2 | AWS RDS | 8 | 50 | 400
| 2.3 | AWS EKS | 1 | 400 | 400
| 2.4 | AWS ELB | 1 | 500 | 500
| 3 | Licensing Cost |  |  |  | 200 | 0.1%
| 3.1 | Google API | 1 | 50 | 50
| 3.2 | Stripe Payment Gateway | 1 | 50 | 50
| 3.3 | Creative Commons | 1 | 50 | 50
| 3.4 | API Licensing | 1 | 50 | 50
| 4 | Raw Material Cost |  |  |  | 23.5 | 0.01%
| 4.1 | Paper Rims | 3 | 0.5 | 1.5
| 4.2 | Pens | 60 | 0.05 | 3
| 4.3 | Files | 40 | 0.1 | 4
| 4.4 | Printing Cost | 500 | 0.03 | 15
| 5 | Transportation Cost | 5 | 5 |  | 25 | 0.01%
|  | Reserves |  |  |  | 119476.5 | 59.04%
|  | Total Cost |  |  |  | 202354
Sheet3
Time-Phased Budget
| S.no | Activity | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | Total
| 1 | Requirement Engineering | 94820 | 107534 |  |  |  | 202354
| 1.1 | Requirement Elicitation | 16720 | 0
| 1.1.1 | Schedule and conduct 3 stakeholder interviews | 3900
| 1.1.1.1 | Interview educators to understand teaching needs | 1200
| 1.1.1.2 | Interview students to identify learning preferences | 300
| 1.1.1.3 | Consult platform providers for technical requirements | 150
| 1.1.2 | Document All Requirements | 3120
| 1.1.2.1 | Perform requirements analysis for the platform | 1500
| 1.1.2.2 | Proofread the requirements document | 120
| 1.1.3 | Research 3 Existing Platforms or Tools | 1600
| 1.1.3.1 | Search by UI components | 300
| 1.1.3.2 | Search by utility relationship | 250
| 1.2 | Requirement Documentation | 6580 | 0
| 1.2.1 | Software Requirement Specification | 4330
| 1.2.1.1 | Create a requirements document template | 150
| 1.2.1.2 | Identify and document functional requirements | 210
| 1.2.1.3 | Identify and document non-functional requirements | 240
| 1.2.1.4 | Document use cases and user stories | 600
| 1.2.1.5 | Capture constraints and dependencies | 400
| 1.2.1.6 | Write all sections that should be present | 480
| 1.3 | Analysis |  | 23370
| 1.3.1 | Analyze high-level requirements |  | 6780
| 1.3.1.1 | Review project objectives and constraints |  | 320
| 1.3.1.2 | Identify key stakeholders' needs and expectations |  | 880
| 1.3.1.3 | Analyze existing platform functionalities |  | 440
| 1.3.1.4 | Decompose high-level requirements into sub-requirements |  | 570
| 1.3.1.5 | Prioritize requirements based on educational goals |  | 400
| 1.3.1.6 | Validate requirements against learning outcomes |  | 200
| 1.3.1.7 | Verify consistency and completeness of requirements |  | 380
| 1.3.1.8 | Resolve requirement conflicts and ambiguities |  | 200
| 1.3.2 | Define detailed requirements |  | 8800
| 1.3.2.1 | Analyze user needs and workflows |  | 720
| 1.3.2.2 | Identify system actors and their roles |  | 760
| 1.3.2.3 | Capture requirements in detail |  | 720
| 1.3.2.4 | Document input and output specifications |  | 540
| 1.3.2.5 | Define acceptance criteria for each requirement |  | 760
| 1.3.2.6 | Ensure requirements align with industry standards |  | 200
| 1.3.2.7 | Validate requirements with stakeholders |  | 400
| 1.3.2.8 | Review and refine requirements |  | 300
| 2 | Project Management |  | 31590 | 3380 |  |  |  | 34970
| 2.1 | Project Planning |  | 31590
| 2.1.1 | Define project objectives and scope along with success criteria |  | 6940
| 2.1.2 | Identify project stakeholders and their roles |  | 1600
| 2.1.3 | Create a work breakdown structure (WBS) |  | 500
| 2.1.4 | Develop project schedule and timeline |  | 300
| 2.1.5 | Determine project resources and budget |  | 800
| 2.1.6 | Plan project communication and collaboration |  | 800
| 2.1.7 | Establish project risk management plan |  | 800
| 2.1.8 | Define project quality management plan |  | 800
| 2.1.9 | Create a product development and testing plan |  | 900
| 2.2 | Project Execution |  | 7050
| 2.2.1 | Assign tasks and responsibilities to team members |  | 2400
| 2.2.2 | Acquire and manage project resources |  | 1200
| 2.2.2.1 | Acquire API Licenses |  | 50
| 2.2.2.2 | Creative Commons Licenses |  | 50
| 2.2.2.3 | Google API's Credentials |  | 50
| 2.2.2.4 | Stripe Payment Gateway's API |  | 50
| 2.2.2.5 | Conduct project kick-off meeting |  | 400
| 2.2.3 | Execute project activities according to the plan |  | 50
| 2.2.4 | Manage project risks and issues |  | 50
| 2.2.5 | Monitor project progress and milestones |  | 50
| 2.2.6 | Hold weekly 1 hour meeting with stakeholders |  | 300
| 2.3 | Project Monitoring and Control |  |  | 3380
| 3 | Design |  |  | 75944 |  |  |  | 75944
| 3.1 | UML and Activity Diagrams |  |  | 5560
| 3.1.1 | Use Case diagram and Use Cases Dressing |  |  | 720
| 3.1.2 | Class Diagram |  |  | 720
| 3.1.3 | Entity Relationship Diagram |  |  | 720
| 3.1.4 | Dataflow Diagram |  |  | 540
| 3.1.5 | Activity Diagram |  |  | 720
| 3.1.6 | Sequence and Collaboration Diagram |  |  | 720
| 3.2 | Database Development |  |  | 29000
| 3.2.1 | Courses Table |  |  | 1000
| 3.2.2 | Users Table |  |  | 1000
| 3.2.3 | Enrollments Table |  |  | 1000
| 3.2.4 | Instructors Table |  |  | 1000
| 3.2.5 | Payments Table |  |  | 1000
| 3.2.6 | Checks, Triggers, and Assertions |  |  | 1000
| 3.2.7 | PL/SQL Stored Procedures and Functions |  |  | 8000
| 3.3 | Architecture Design |  |  | 12200
| 3.3.1 | Define the overall system architecture |  |  | 800
| 3.3.2 | Identify the necessary components and modules |  |  | 2000
| 3.3.3 | System Architecture Diagram |  |  | 4000
| 3.3.3.1 | High-level Architecture Diagram |  |  | 800
| 3.3.3.2 | Layered Architecture Diagram |  |  | 800
| 3.3.4 | Determine the technology stack for each layer |  |  | 200
| 3.3.5 | Ensure scalability and performance considerations |  |  | 200
| 3.3.6 | Plan for integration with external systems/APIs |  |  | 200
| 3.4 | UI Designing (React UI Instructions) |  |  |  | 14349
| 3.4.1 | Main Screen Design |  |  |  | 162.5
| 3.4.1.1 | Login Button |  |  |  | 32.5
| 3.4.1.2 | Signup Button |  |  |  | 32.5
| 3.4.2 | Log-In Page |  |  |  | 650
| 3.4.2.1 | Username, Password, Remember Me Input Fields |  |  |  | 65
| 3.4.2.2 | Login As: (Admin, Instructor, Student, General Public) Selection |  |  |  | 32.5
| 3.4.2.3 | Login Button, Sign-Up Button |  |  |  | 65
| 3.4.3 | Sign-Up Page |  |  |  | 253.5
| 3.4.3.1 | Email, Username, Password, Confirm Password |  |  |  | 84.5
| 3.4.3.2 | Sign Up Button, Login Button, Back Button |  |  |  | 19.5
| 3.4.4 | Admin Page |  |  |  | 1183
| 3.4.4.1 | Navbar: (Add Courses, View Enrollments, Info, Update Company, Deletion Log) |  |  |  | 130
| 3.4.4.2 | Courses Information Table |  |  |  | 130
| 3.4.4.3 | Delete Button |  |  |  | 130
| 3.4.5 | Add New Course Page |  |  |  | 676
| 3.4.5.1 | Name of Course |  |  |  | 32.5
| 3.4.5.2 | Description, Instructor |  |  |  | 13
| 3.4.5.3 | Duration, Price, Category |  |  |  | 65
| 3.4.5.4 | IDs (Cid, Cname, Instructor, Price) |  |  |  | 130
| 3.4.6 | Unapproved Enrollments List Page |  |  |  | 325
| 3.4.6.1 | Name of Student |  |  |  | 65
| 3.4.6.2 | Course Name, Enrollment Status |  |  |  | 32.5
| 3.4.6.3 | Approve Button, Reject Button |  |  |  | 32.5
| 3.4.7 | Update Course Page |  |  |  | 746
| 3.4.7.1 | Name of Course |  |  |  | 260
| 3.4.7.2 | Description, Instructor |  |  |  | 13
| 3.4.7.3 | Duration, Price, Category |  |  |  | 65
| 3.4.7.4 | IDs (Cid, Cname, Instructor, Price) |  |  |  | 130
| 3.4.8 | Deletion Log Page (For Courses Deletion) |  |  |  | 468
| 3.4.9 | Logout Button on All Pages |  |  |  | 50
| 3.4.10 | Student-Friendly Courses |  |  |  | 130
| 3.4.11 | Instructor-Friendly Courses |  |  |  | 130
| 3.4.12 | Student Courses |  |  |  | 260
| 3.4.13 | Instructor Courses |  |  |  | 260
| 4 | Implementation |  |  |  |  | 0 | 0 | 0 | 0 | 0
| 4.1 | Login Page Connectivity with Database Verification |  |  |  |  | 0
| 4.2 | Company Login Page Connectivity with Database |  |  |  |  | 0
| 4.3 | Home Page Rendering with Real-Time Data | [5 empty] | 0
| 4.4 | Dynamic Statistics Updates and Rendering with Real-Time Data | [5 empty] | 0
| 4.5 | Penalty/Tax Calculation Rules Setting, Validation of Data | [5 empty] | 0
| 4.6 | Company Data Upload, Data Fetching Module Implement | [5 empty] | 0
| 4.7 | Public Website and Emission Data Analytics Page Implement | [5 empty] | 0
| 4.8 | Emission and Waste Statistics | [5 empty] | 0
| 4.9 | Eflag and Wflag Logic Implementation | [5 empty] | 0
| 4.1 | Company Data Verification/Approval Implementation | [5 empty] | 0
| 4.11 | Deletion Log Implementation | [5 empty] | 0
| 4.12 | Exception Handling | [6 empty] | 0
| 5 | Testing | [8 empty] | 0 | 0
| 5.1 | Smoke Testing for Every Feature | [8 empty] | 0
| 5.2 | Unit Testing | [8 empty] | 0
| 5.3 | Integration Testing | [8 empty] | 0
| 5.4 | Regression Testing (After Every Change) | [8 empty] | 0
| 5.5 | System Testing | [8 empty] | 0
| 5.6 | Acceptance Testing | [8 empty] | 0
| 5.6.1 | White Box Testing | [8 empty] | 0
| 5.6.2 | Black Box Testing | [8 empty] | 0
| 5.6.3 | Beta Testing | [8 empty] | 0
| 6 | Deployment | [9 empty] | 0 | 0
| 6.1 | AWS EC2 Instance | [9 empty] | 0
| 6.2 | AWS ELB (Elastic Load Balancer and Autoscaling) | [9 empty] | 0
| 6.3 | AWS EKS (Kubernetes (EKS)) | [9 empty] | 0
| 6.4 | AWS S3 Storage | [9 empty] | 0
| 6.5 | AWS VPC Configuration | [9 empty] | 0
| 6.6 | AWS AMI Installation | [9 empty] | 0
| 6.7 | Website Hosting and Deployment | [9 empty] | 0
| 7 | Transportation Cost | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 25
| 8 | Raw Material Cost | 5.88 | 5.88 | 5.88 | 0 | 0 | 0 | 5.88 | 23.5
| 9 | Component Cost |  |  | 1301 |  |  |  | 1301
| 10 | Overhead Cost (15% of Labour Cost) | 2620.77 | 2620.77 | 2620.77 | 2620.77 | 0 | 0 | 0 | 10483.07
| 11 | Project Team Meetings Cost | To be Added Separately (20 meetings) | [9 empty] | 1800
|  | Monthly Total Cost | 97451.65 | 111065.65 | 83259.65 | 16974.77 | 0 | 0 | 5.88 | 308757.57